## ProjectSchedule
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Paragon International University Admission System | [5 empty] | SIMPLE GANTT CHART by Vertex42.com
Enter Company Name in cell B2. | Company Name: Group #12 | [5 empty] | https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. | Project Lead Develper: Juden Ung, Leapheng Khy,Sakvipubp Suy,Sihak Vityea Sam | Project Start: |  | 2021-11-26
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  | 1 |  |  | 2021-11-22 | [6 empty] | 2021-11-29 | [6 empty] | 2021-12-06 | [6 empty] | 2021-12-13 | [6 empty] | 2021-12-20 | [6 empty] | 2021-12-27 | [6 empty] | 2022-01-03 | [6 empty] | 2022-01-10
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2021-11-22 to 2022-01-16
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2021-11-22 to 2022-01-16
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Phase 1 Title: Group meeting and System Analysis
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Plan and discuss | Everyone | 100% | 2021-11-26 | 2021-11-27 | 2
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Design and Draft Layout | Sakvipubp Suy | 100% | 2021-11-27 | 2021-11-29 | 3
| Server Rent | Sihak Vityea Sam | 100% | 2021-11-27 | 2021-11-28 | 2
| Communicate with sponsors | Juden Ung | 100% | 2021-11-27 | 2021-11-28
| Buying equipement related to project | Leapheng Khy | 100% | 2021-11-28 | 2021-11-29
| Finish analysis | Everyone | 100% | 2021-11-29 | 2021-11-30 | 2
Phase 2 Title: Designing the First prototype
| Divide the task | Everyone | 50% | 2021-12-01 | 2021-12-02
| Design the web page with basic structure | Sakvipubp Suy | 0% | 2021-12-02 | 2021-12-04
| Design the list selection box for users to select | Sihak Vityea Sam | 0% | 2021-12-02 | 2021-12-02
| Meet to confirm first prototype | Everyone | 0% | 2021-12-04 | 2021-12-04
Phase 3 Title: Design Content for undergraudate
| Application process | Juden Ung | 0% | 2021-12-04 | 2021-12-11 | 8
| Information about majors with every details | Sakvipubp Suy | 50% | 2021-12-04 | 2021-12-05 | 2
| Brochure/Prospectus | Sihak Vityea Sam | 0% | 2021-12-04 | 2021-12-06 | 3
| Online Application Form | Leapheng Khy | 0% | 2021-12-04 | 2021-12-06 | 3
Phase 4 Title: Design Content For Postgraduate
| Application process | Leapheng Khy | 0% | 2021-12-11 | 2021-12-16 | 6
| Embed Brochure/Prospectus | Sakvipubp Suy | 0% | 2021-12-11 | 2021-12-12 | 2
| Online Application Form | Sihak Vityea Sam | 0% | 2021-12-11 | 2021-12-12 | 2
| Design and Display Display Information about Postgraduate Program | Sakvipubp Suy | 0% | 2021-12-12 | 2021-12-13 | 2
Phase 5 Title: Design Content For International
| Request Information Process | Sihak Vityea Sam | 0% | 2021-12-16 | 2021-12-20 | 5
| Design and Display Information for international Student | Sakvipubp Suy | 0% | 2021-12-16 | 2021-12-17 | 2
Phase 6 Title: Design Content for Tuition Fees
| Design and Display Fees for Undergraduate Degreees | Sakvipubp Suy | 0% | 2021-12-20 | 2021-12-21 | 2
| Design and Display Fees for Postgraduate programs | Sakvipubp Suy | 0% | 2021-12-20 | 2021-12-21 | 2
This is an empty row | Design and Display Fees for Cost of Living in Phnom Penh | Sakvipubp Suy | 0% | 2021-12-20 | 2021-12-21
Phase 7 Title: Design Content for Currently Available Scholarships
| Application Process for Rector Scholarship | Leapheng Khy | 0% | 2021-12-22 | 2021-12-29
| Drag and drop file Function for the appiication form | Sihak Vityea Sam | 0% | 2021-12-22 | 2021-12-24
| Design and display Information for Partnership Scholarships | Leapheng Khy | 0% | 2021-12-25 | 2021-12-29
Phase 8 Title: Design Content for Currently Available Scholarships
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Display list of information regarding scholarships | Sakvipubp Suy | 0% | 2021-12-30 | 2022-01-03
Phase 9 Title: Other essential designs
| Design user interface | Sihak Vityea Sam | 0% | 2022-01-04 | 2022-01-14
| Design database to store information from user | Everyone | 0% | 2022-01-08 | 2022-01-18 | 11
| Design payment method | Everyone | 0% | 2022-01-08 | 2022-01-18
| Design system Software platform(Ios, andriod, window, ...) | Everyone | 0% | 2022-01-05 | 2022-02-04 | 31
| Check for other designs | Leapheng Khy | 0% | 2022-02-05 | 2022-02-06 | 2
| Finished Designs | Everyone | 0% | 2022-02-07 | 2022-02-08 | 2
Phase 10 Title: Development
| Develop the system by integrating database, system software and web together | Everyone | 0% | 2022-02-09 | 2022-02-10 | 2
| Perform initial testing | Everyone | 0% | 2022-02-10 | 2022-02-13 | 4
| Finish testing | Everyone | 0% | 2022-02-14 | 2022-02-15 | 2
Phase 11 Title: Testing
| Connecting physical equipment to the system | Sihak Vityea Sam | 0% | 2022-02-16 | 2022-02-17 | 2
| Performing system Testing | Everyone | 0% | 2022-02-17 | 2022-02-18 | 2
| Take note of the isssue | Everyone | 0% | 2022-02-18 | 2022-02-20 | 3
| Correcting issues found | Everyone | 0% | 2022-02-20 | 2022-02-22 | 3
| Testing Finished | Everyone | 0% | 2022-02-22 | 2022-02-23 | 2
Phase 12 Title: Implementation
| On site installation | Juden Ung | 0% | 2022-02-24 | 2022-02-25 | 2
| Implement plan to support the system | Everyone | 0% | 2022-02-26 | 2022-02-27 | 2
Phase 13 Title: Completion
| System Maintainance and update | Everyone | 0% | Once In | Every week | #VALUE!
Insert new rows ABOVE this one

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.